## CHURCH OUTSIDE WORK
CHURCH, OUTSIDE 2020 SPRING LIST
| JOB | TOOLS/MATERILS |  | PERFORMED BY
1 | The control wires for the two air conditioners outside the Lower Level CLC have been exposed to the UV light from the sun for 15 years and deteriorating badly. They should be replaced and covered with some type of conduit to protect them in the future. | New conduit, new HVAC control wire, tie wraps, wire strippers, wire nuts, pliers, screwdrivers,
2 | The 20 year old fence blocking the view of the air conditioner ducts on the south side of the Sanctuary is in bad shape. When the wind blows the top portion moves with the breeze. Investigate, possibly replace the entire panels with new ones. The town required the fence, so just removing it is not an option. | This fence has been repaired in the past, it is constructed of two 6 ft x 8 ft panels and 3 posts that support the sections. Unfortunately the wood has warped over time making it difficult to reconstruct. The idea is to replace the entire sections with vinyl sections. We would need a pick-up truck to deliver the panels, and then construct the new vinyl sections in place between the posts.
3 | Install the new security camera at the end of the overhang by door #1. The wire has already been run from the office to the fire doors at the east end of Mercer Hall. Remove the bracket to hang a flag in on the end of the overhang and install the new camera in it's place. | New camera, ladders, drill and bits to make a hole in the wall to run the cable outside. Approx. 50 ft of metal conduit prepainted a tan color, conduit retention clips, screwdrivers, electrical fish tape, numerous connectors for the conduit, wire strippers, screws to retain the retention clips and the camera. This job is completed when the camera is installed. The Trustees will attach the camera to the wire, aim and focus it and connect the other end to the appropriate equipment.
4 | Rebuild the cover over the air intake for the boiler room. Currently the roof slopes to the north and slightly to the west. Due to the west slope, water runs down the wall of the air shaft into the boiler room when it rains hard. | Level the base of the air intake so the roof of the unit tilts slightly east and to the north. Then attach a right angle flashing on the east side of the roof against the building to assure that no water runs down the side of the building into the air intake below, and then into the boiler room. Seal the joint between the building and the flashing with long life caulking.
5 | There are four large metal grates protecting the horizontal A/C ducts south of the Sanctuary from falling snow in the winter. These grates are rusting. With four people remove the grates from their present location, place them in the grass. Brush the rust off them with a metal brush while wearing safety glasses, then paint both upper and lower surfaces. When completed and dry have four people help reposition the grates back to their original location. | Four strong people, wire brush (possibly wire brush on end of a drill) , safety glasses, paint, disposable paint brushes, can opener, papers, paper towels, old clothes, hammer, possible sun screen. CAREFUL- The Rust-Oleum paint is oil based and difficult to clean up. Paint the unit with Rusty metal primer first, let dry for 24 hours before painting with gray Rust Oleum paint. Wear old clothes.
6 | Paint the gas pipes on the flat roof over the entrance area (Door #2) with yellow paint as they are rusting. CAUTION when working on the flat roof, the roof is a 1/4 in thick membrane that has a rubber base, therefore it is soft and a hole can be made in it easily with sharp objects, resulting in a leak. Make sure someone else is within the sound of your voice in case you need help for any reason. There are five heating units on this roof, therefore five spurs of the gas line to be painted. | Wearing safety glasses, remove the rust off the pipes with a wire brush, then clean off the dirt and paint the gas pipes with Rusty metal primer. Allow to dry 24 hours before using the yellow Rust Oleum paint. Tools- Wire brush to remove rust, drop cloth to cover the area under the pipe being painted, rags to clean off the surface to be painted, disposable paint brushes or a small disposable rollers, can of Rusty metal primer and yellow paint, screwdriver to open paint can, hammer to close paint can, newspaper for under the bucket. Paper towels. Access the roof by placing the base of an extension ladder close to the bench outside door #2. Caution, the paint is oil based, therefore difficult to clean up. Wear old clothes.
7 | Paint the gas pipes on the flat roof over the KITCHEN area with yellow paint as they are rusting. CAUTION when working on the flat roof, it is a 1/4 in thick membrane that has a rubber base, therefore the roof is soft and a hole can be made in it easily with sharp objects, resulting in a leak. Make sure someone else is within the sound of your voice in case you need help for any reason. There are three heating units on this roof, therefore three spurs of the gas line to be painted. | Wearing safety glasses, remove the rust off the pipes with a wire brush, then clean off the dirt and paint the gas pipes with Rusty metal primer. Allow to dry 24 hours before using the yellow Rust Oleum paint. Tools- Wire brush to remove rust, drop cloth to cover the area under the pipes being painted, rags to clean off the surface to be painted, disposable paint brushes or small disposable rollers, can of Rusty metal primer and yellow paint, screwdriver to open paint can, hammer to close paint can, newspaper for under the can. Paper towels. Access the roof by a permanent ladder located in the south west corner of the CLC store room. Caution, the paint is oil based, therefore difficult to clean up. Wear old clothes.
8 | Paint the steel beam over door #2, it is starting to rust. | Extension ladder, proper color exterior paint, wire brush, safety glasses, drop clothes for the sidewalk, cloth to clean beam after removing rust, paint brush, paint can lid remover, hammer to reinstall lid on paint can, paper towels. This is latex paint, therefore water clean-up.
9 | On the west end of the CLC roof, over the kitchen, the copper trim has come off in several places. Re attach the copper trim with tap con masonry screws into the brick. The trim was initially held in place with small nails secured into the edge of the plywood supporting the roof. The hardest part of this job is getting an extension ladder onto the flat roof in order to reach the areas that need to be repaired. Two people are needed for this job for safety and to manage the ladder up to the roof. | Tools- light weight aluminum extension ladder, hammer drill, drill bits, tap con masonry screws, extension cord, 1/4 inch driver for screws, copper trim that is laying on the kitchen roof.
10 | Remove the grass that is under the furnace exhaust vent on the west end of the CLC close to the dumpster. Place black plastic down and then cover the area with some of the patio block that are in the dumpster enclosure to prevent grass from growing in the area. Hopefully this will stop the damage to the vent pipe by the lawnmowers. | Shovel, rake, black plastic sheeting, scissors, tape measure, leather gloves, several patio blocks, rubber hammer to assure the blocks are flat and level, knee pads. Possibly wheel barrow to remove excess dirt.
11 | Install some cold patch in the area the parking lot is deteriorating just west of the kitchen. | Done | Done
11 | Take apart the worst rotted 8 foot long picnic table behind the CLC for spare parts. | Tools- Large wrenches, large socket sets, leather gloves, ability to work with 2x10x 8 feet long lumber. Skill saw to cut up the rotted pieces of lumber and dispose of it in the dumpster. Caution- one of the tables is only 6 ft long, do not take this table apart as it's parts are totally different than the remaining 5 tables.
| There are several small gaps in the cement foundation of the Sanctuary, just north of the front spigot that is used to water the Memorial Garden. | Patching cement, bucket to mix a small amount of cement in, cement trowel.
| Caulk the top of the aluminum frame around the window at the south end of the lower hall in the Education wing. Water comes in when it rains | Ladder, putty knife, prop to hold door open, tube of caulking and caulking gun, paper towels. Be careful not to hit your head on the bottom of the fire escape just above the window.
#REF!
#REF! | Clear the brush growing in the area under the electrical wires along the south border |  | Boy Scouts
#REF! | In the South west corner of the parking lot, there are a number of 6 to 12 foot trees starting to grow in the area of the tall grass. Cut these small trees down and drag the branches into the woods to the south so the area of the tall grass could be cut with a mower at some time. | Long pants, leather gloves, loppers, bow saw, wheel barrow | Boy Scouts
jobs for some other time
#VALUE! | Remove rust off the six sign poles around the grass island , and repaint the poles. | Old clothes, Safety goggles to be worn when removing rust off poles with steel brush, cloth to clean dust off poles, rust resistant paint, disposable paint brush, paper towels, paint can top remover, hammer to reseal top on can
| Two wood posts toward the east end of the driveway by Livernois Road were knocked over .Replace the posts. | Install two new posts at this location. Pick, shovel, dig a hole for each pole, install the new posts. Run the rope through the holes in the top of each post. When other work is complete, compress the soil around each post and clean up. (posts in bell tower)
#VALUE! | Rebuild the top of the 5 benches on the east end of the grass island with composite "wood", remove the existing real wood. | New plastic composite "wood" to replace existing wood. Circular saw, outdoor fasteners, screwdriver, measuring tape
1 | South education wing of 1963 building, around the top of the building, just below the flat roof, there is a wood board. There are two issues with the board, one it needs to be protected, two- it covers a gap between the top of the brick wall and the roof where wind blows into the ceiling of the building. It must be sealed behind the board and the building to keep the cold winds out in the winter. | Water soluble foam filler behind the board, some type of vinyl siding or something to cover the wood .
2 | The wood steps outside the carpeted steps in the 1963 wing are starting to deteriorate and some aren't stable, rebuild them.
#REF!
#REF!
#REF!

## CHURCH INSIDE WORK
CHURCH, 2020 SUMMER LIST
| JOB | TOOLS/MATERILS | PERFORMED BY
OUTSIDE LIST
1 | The control wires for the two air conditioners outside the Lower Level CLC have been exposed to the UV light from the sun for 15 years and are deteriorating. They should be replaced and covered with some type of conduit to protect them in the future. | New conduit, new HVAC control wire, tie wraps, wire strippers, wire nuts, pliers, screwdrivers,
2 | The 20 year old fence blocking the view of the air conditioner ducts on the south side of the Sanctuary is in bad shape. When the wind blows the top portion moves with the breeze. The town required the fence, so just removing it is not an option. DONE | This fence has been repaired in the past, it is constructed of two 6 ft x 8 ft panels and 3 posts that support the sections. Unfortunately the cross members have shifted and detached from the wood end supports. Center the cross members, re attach the end pieces to the cross members, then re secure the panel to the 4x4 posts that hold the sections up with very long outdoor wood screws. Hammers, various length outdoor wood screws, battery powered driver, level, probably two people, one to steady one side when the other drives screws into the structure.
3 | Install the new security camera at the end of the overhang by door #1. The wire has already been run from the office to the fire doors at the east end of Mercer Hall. Remove the bracket to hang a flag in on the end of the overhang and install the new camera in it's place. | New camera, ladders, drill and bits to make a hole in the wall to run the cable outside. Approx. 50 ft of metal conduit pre-painted a tan color, conduit retention clips, screwdrivers, electrical fish tape, numerous connectors for the conduit, wire strippers, screws to retain the retention clips and the camera. This job is completed when the camera is installed. The Trustees will attach the camera to the wire, aim and focus it and connect the other end to the appropriate equipment.
4 | Rebuild the cover over the air intake for the boiler room. Currently the roof slopes to the north and slightly to the west. Due to the west slope, water runs down the wall of the air shaft into the boiler room when it rains hard. | Level the base of the air intake so the roof of the unit tilts slightly east and to the north. Then attach a right angle flashing on the east side of the roof against the building to assure that no water runs down the side of the building into the air intake below, and then into the boiler room. Seal the joint between the building and the flashing with long life caulking.
5 | There are four large metal grates protecting the horizontal A/C ducts south of the Sanctuary from falling snow in the winter. These grates are rusting. With four people remove the grates from their present location, place them in the grass. Brush the rust off them with a metal brush while wearing safety glasses, then paint both upper and lower surfaces. When completed and dry have four people help reposition the grates back to their original location. | Four strong people, wire brush (possibly wire brush on end of a drill) , safety glasses, paint, disposable paint brushes, can opener, papers, paper towels, old clothes, hammer, possible sun screen. CAREFUL- The Rust-Oleum paint is oil based and difficult to clean up. Paint the unit with Rusty metal primer first, let dry for 24 hours before painting with gray Rust Oleum paint. Wear old clothes.
6 | Paint the gas pipes on the flat roof over the entrance area (Door #2) with yellow paint as they are rusting. CAUTION when working on the flat roof, the roof is a 1/4 in thick membrane that has a rubber base, therefore it is soft and a hole can be made in it easily with sharp objects, resulting in a leak. Make sure someone else is within the sound of your voice in case you need help for any reason. There are five heating units on this roof, therefore five spurs of the gas line to be painted. | Wearing safety glasses, remove the rust off the pipes with a wire brush, then clean off the dirt and paint the gas pipes with Rusty metal primer. Allow to dry 24 hours before using the yellow Rust Oleum paint. Tools- Wire brush to remove rust, drop cloth to cover the area under the pipe being painted, rags to clean off the surface to be painted, disposable paint brushes or a small disposable roller, can of Rusty metal primer and yellow paint, screwdriver to open paint can, hammer to close paint can, newspaper for under the bucket. Paper towels. Access the roof by placing the base of an extension ladder close to the bench outside door #2. Caution, the paint is oil based, therefore difficult to clean up. Wear old clothes.
7 | Paint the gas pipes on the flat roof over the KITCHEN area with yellow paint as they are rusting. CAUTION when working on the flat roof, it is a 1/4 in thick membrane that has a rubber base, therefore the roof is soft and a hole can be made in it easily with sharp objects, resulting in a leak. Make sure someone else is within the sound of your voice in case you need help for any reason. There are three heating units on this roof, therefore three spurs of the gas line to be painted. | Wearing safety glasses, remove the rust off the pipes with a wire brush, then clean off the dirt and paint the gas pipes with Rusty metal primer. Allow to dry 24 hours before using the yellow Rust Oleum paint. Tools- Wire brush to remove rust, drop cloth to cover the area under the pipes being painted, rags to clean off the surface to be painted, disposable paint brushes or small disposable roller, can of Rusty metal primer and yellow paint, screwdriver to open paint can, hammer to close paint can, newspaper for under the can. Paper towels. Access the roof by a permanent ladder located in the south west corner of the CLC store room. Caution, the paint is oil based, therefore difficult to clean up. Wear old clothes.
8 | Paint the steel beam over door #2, it is starting to rust. | Extension ladder, proper color exterior paint, wire brush, safety glasses, drop clothes for the sidewalk, cloth to clean beam after removing rust, paint brush, paint can lid remover, hammer to reinstall lid on paint can, paper towels. This is latex paint, therefore water clean-up.
9 | On the west end of the CLC roof, over the kitchen, the copper trim has come off in several places. Re attach the copper trim with tap con masonry screws into the brick. The trim was initially held in place with small nails secured into the edge of the plywood supporting the roof. The hardest part of this job is getting an extension ladder onto the flat roof in order to reach the areas that need to be repaired. Two people are needed for this job for safety and to manage the ladder up to the roof. | Tools- light weight aluminum extension ladder, hammer drill, drill bits, tap con masonry screws, extension cord, 1/4 inch driver for screws, copper trim that is laying on the kitchen roof.
10 | Remove the grass that is under the furnace exhaust vent on the west end of the CLC close to the dumpster. Place black plastic down and then cover the area with some of the patio block that are in the dumpster enclosure to prevent grass from growing in the area. Hopefully this will stop the damage to the vent pipe by the lawnmowers. | Shovel, rake, black plastic sheeting, scissors, tape measure, leather gloves, several patio blocks, rubber hammer to assure the blocks are flat and level, knee pads. Possibly wheel barrow to remove excess dirt.
11 | Install some cold patch in several areas north of the Sanctuary as the area in the exit lane is deteriorating and needs some attention. | Several locations are "alligatoring " and are breaking up into small pieces. These small pieces then come out and form a hole in the surface. Dump several bags of "cold patch" in these Ares and smooth it out with the back of a rake. Then tamp it down with the tamping tool. Wear old shoes for this project Several bags of cold patch, rake, and tamper.
12 | Take apart the worst rotted 8 foot long picnic table behind the CLC for spare parts. | Tools- Large wrenches, large socket sets, leather gloves, ability to work with 2x10x 8 feet long lumber. Skill saw to cut up the rotted pieces of lumber and dispose of it in the dumpster. Caution- one of the tables is only 6 ft long, do not take this table apart as it's parts are totally different than the remaining 5 tables.
13 | Spray the weeds in the sitting area on the grass island north of the Sanctuary, the weeds in the sidewalk leading out to Livernois, and the weeds in the sidewalk along Livernois. | The sprayer, weed control, and rubber gloves are located in the base of the bell tower. Mix up 2 gallons of spray, pump the unit up and then proceed to spray unwanted weeds.
14 | There are several taller dead trees close to the power lines on the south border, just east of the playground area. Carefully cut the dead trees down and have them fall away from the wires. Cut up the dead trees and dispose of the remains in the woods to the south. | Rope to attach to the trees to help guide them in the desired direction when they start to fall. Chain saw, 2 cycle gas, bar oil, tools to tighten the tension on the chain, gloves, 2nd person to pull the rope when the tree starts to fall.
CHURCH INSIDE JOB LIST
1 | Replace the following burnt out fluorescent tubes; 2 tubes in room 111 and one tube in the restroom off of room 118. and 1 tube in the kitchen pantry Replace with LED tubes | New LED light tubes, ladder, knowledge how to open the light fixture. Depress the two tabs on one side of the cover on the fixture and the bottom cover should swing open, held in place by two hinges on the other side of the fixture. If you replace a burnt out tube and it still doesn't function, the ballast is probably bad. Make a note of what light it is and keep going. Keep the burnt out tubes separate, and dispose of them in the dumpster when done. Provide the trustees any feed back about fixtures that would not light even with a new tube. (note if there is a bad ballast, either the two outside tubes will not light, or the one center tube will not light. There are two separate ballasts in each fixture)
2 | Replace the batteries in numerous clocks throughout the building. A number of the battery powered clocks are displaying the incorrect time. On these units replace the battery and reset the clock. If the clock is displaying the correct time, use a battery tester to see if the battery is good, or should be replaced. | Battery tester, large container of new AA batteries, short light weight ladder The majority of the clocks are located in class rooms 100 through 111, the theater, and outside of it, class rooms 203 to 209, the office and the kitchen. In the kitchen please reset the clocks on the stoves as well.
2 | The center left door into the Sanctuary from the Narthex doesn't close all the way at times. Remove some wood off the top of the door to correct the situation Mark the top of the door where it binds. | Detach the hold open arm on top, don't adjust anything. Then remove the hinge pins and remove the door. Take it outside and sand the top of the door with a belt sander. Re install the door and hinge pins. Assure it functions properly before attaching the hold open arm again. Ladder, screwdrivers, pencil, strong people, hammer, belt sander, extension cord.
3 | The toilet seat in the zzz restroom is loose. | Proper size wrench to tighten nuts on the bottom.
3 | In the narthex, on the west wall, south end, there was a wreath hung on the wall with an adhesive backed hook. The hook fell down. Replace the hook and re hang the wreath. | New hook, tape measure, pencil
3 | Replace a duplex electrical outlet at the north end of the hall in the upper story of the Education building (outside room 204) The current outlet is worn out and will not retain a plug well. | Turn the breaker to the outlet off. The breaker is located in the hall outside of room 203. Remove the cover plate, and the existing duplex outlet, install the new duplex outlet. Test for proper grounding and polarity with an outlet tester. Re install the cover plate. Light, screwdrivers, duplex outlet, needle nose pliers, outlet tester. Connect the black wire to the brass color screw in the outlet and the white wire to the silver color screw in the outlet.
4 | Paint the steel pole that the exterior doors latch against at door #1 with rust preventive paint. They are exposed to salt during the winter and are rusting | Steel brush to remove rust, then clean the pole. Apply the rust preventing paint which is not water removable. Use a disposable paint brush and prepare the area well before applying the paint. Install multiple signs close to the poles after painting them "wet paint"
5 | Damage was being done to the wall in room 116 due to the material being stored in there. The material has now been relocated. Repair the wall with spackle and sand it when dry. | Pad to kneel on, sand the area first , then spackle, spackle knife, , screwdriver to open spackle container. Let the spackle dry, it will be painted later.
6 | Touch up the east wall of room 110 (youth room) just above the tables along the wall with woodruff tan eggshell paint. | Eggshell woodruff paint found in a 5 gallon bucket, paint brush paint stirrer, screwdriver to remove plastic lid off bucket, newspapers, paper towels
7 | In the room 111, adjacent to room 110 there is damage to the wall under the light switch. Fill in the gash with spackle, clean the wall with Mr. Clean pads, and then touch up the wall with Eggshell Woodruff paint | Spackle, putty knife, Mr. clean eraser to clean wall to find defects, water to put eraser in occasionally, Sand paper. If everything dries in time, paint the area with Eggshell Woodruff paint found in a 5 gallon bucket.
8 | At the bottom of the carpeted steps there are multiple ceiling tiles damaged by moving to turn valves above the ceiling. | Ladder, can of special ceiling tile spray paint, newspapers
10 | The bathroom in room 207 has a rust streak on the wall below the toilet water supply line. Also a rust spot on the floor. Use Mr. Clean or SOS pads to remove the rust | SOS or Mr. Clean pad and paper towels.
11 | In the lower level Men's room, there is a rust streak on the south wall under the water feed pipe for the Sloan valve. Remove the rust streak with a Mr. Clean pad or an SOS pad. | SOS or Mr. Clean pad and paper towels.
12 | At the south end of the lower level hall in the education building (by rooms 105 and 106), there is an exit door to the outside. There are weeds etc. growing up in the exit stairwell and leaves covering the drain. Remove the weeds and the leaves . | Prop the door open with an object and remove the weeds and the leaves off the floor. Dust pan, dust brush, gloves to pull the weeds out with. Dispose the weeds in the woods to the south.
12 | Clean out the workroom
13 | Repair stools in workroom | Numerous stools have loose legs. Align the legs in the proper location, possibly holding in place with a clamp, Drill holes through the top and through the leg, Insert a carriage bolt from the top, through the leg and then insert a washer on the end of the bolt, Secure the bolt with a nut.
14 | Remove one ballast and replace the emergency power supply in fluorescent fixtures. Install 12 direct connect LED light tubes in fixtures that are on 24hours/ day THAT HAVE A SMALL RED LIGHT IN THE FIXTURE. Most of these lights are in the lower halls. Replace the three fluorescent tubes with LED tubes. 3 tubes in hall by room 117 (Mechanical Room) 3 tubes in hall close to room 111 and fire doors, 3 tubes in hall by room 110 (Youth room) 3 tubes in hall by room 109 (Resource room) | Only work on the 24 hours/day lights that have a small black Emergency Light Button and also a red light visible in the fixture with three fluorescent tubes in it. Drop down the cover on hinges, remove the cover over the ballasts, Remove the two existing ballasts. There are 3 pages of instructions as how to perform this job step by step. Please obtain them from the job table. Fiberglass ladder, turn electric off to the light at the breaker box in room 116, auxiliary light to see when the power is off, wire cutters, wire nuts, screw drivers, power tester, knowledge of electrical wiring, new LED light tubes, new Ni-cd emergency battery, labels to place on light fixture wired for DIRECT CONNECT LED tube that have two hot ends. Two experienced people to do this job.
14 | Replace approximately six old hooks on the wall in the Resource room (Room 109) with newer, flatter hooks that are safer. | New hooks, screwdrivers, battery powered drill, new fasteners to hold hooks securely to the wall, drill bits, level, pencil.
15 | Replace approximately eight old hooks on the wall in the shower room located at the extreme west end of the lower level CLC. The new hooks are flatter and safer. | New hooks, screwdrivers, battery powered drill, new fasteners to hold hooks securely to the board, drill bits, level, pencil.